## Basic Picture
Basic timeline overview
Decisions Needed
Internal processes, data gathering, SIP drafting
Formal Public Process
SIP Released for Public comment
Internal process,
EPA submittal
Due Date

## Initial
Start with your individual process for public notice, adoption and submittal to EPA and then work backword to figure out your timelines.
Assume Due date to EPA is November 2027
SIP/Reg Adoption Submission Schedule
|  |  |  | 1 |  |  | SIP Finished, release
| Release SIP/Regulations (49 days) | X*+X days |  |  |  |  | 2026-11-01
| Date for hearing date request | X | + | 25 |  |  | 2026-11-26
| Hearings (federal requirement) | X | + | 32 | - | 37 | 2026-12-03 | - | 2026-12-08
| Question ending date | X | + | 37 | - |  | 2026-12-08
| Post response to questions | X | + | 48 | - |  | 2026-12-19
| Public Notice Ends | X | + | 49 | - |  | 2026-12-20
| Response to Comments | 30 days | + | 80 | - |  | 2027-01-20
| Review and Adoption by Commissioner | 30 days | + | 110 | - |  | 2027-02-19
| DOL Review/Review committee (6 months) | Give to DOL | + | 290 | - |  | 2027-08-18
| DOL Review Completed (10 days) | 10 days | + | 300 | - |  | 2027-08-28
| File by Lt. Gov | 14 days | + | 314 | - |  | 2027-09-11
| Send Filed Regulations and SIP to EPA | 30 days | + | 344 | - |  | 2027-10-11
Local
|  | X | + | 1 | - |  | 2026-11-01
|  | 30 days | + | 41 | - |  | 2026-12-12
|  | 14 days | + | 55 | - |  | 2026-12-26
|  | 14 days | + | 69 | - |  | 2027-01-09
|  |  | + | 76 | - |  | 2027-01-16
|  | 14 days | + | 90 |  |  | 2027-01-30 |  |  | +

## Detailed picture
Request Data from Sources
Identify and start surveys
Detailed timeline
Decisions Needed
Regulation packages started— measures included in SIP
Formal Public Process
SIP Released for Public comment
30-day review by EPA
Legal review, Filing,
SIP Adoption
SIP Development Plan
IPP
TAP
Initial Communication Plan
Submit to EPA

## Detailed schedule
Start with your individual process for public notice, adoption and submittal to EPA and then work backword to figure out your timelines.
Assume Due date to EPA is November 2027
SIP Development example schedule
Start SIP Development
| Internal Meeting with staff to discus | X*+X days |  |  |  |  | 2023-11-03
| Draft SIP Development Plan, IPP, TAP Initiall Communcation Plan | X | + | 25 |  |  | 2023-11-28
| Meet with EPA | X | + | 28 | - | 29 | 2023-12-01 | - | 2026-12-02
| Request for Information from Sources, conduct surveys, gather data | X | + | 30 | - |  | 2023-12-03
| All data due to office | X | + | 365 | - |  | 2024-11-02
| Stakeholder input? | 45 days | + | 410 | - |  | 2024-12-17
| Drafts with preliminary release? | 30 days | + | 441 | - |  | 2025-01-17
| Draft SIP chapters and appendix | 365 days | + | 806 | - |  | 2026-01-17
| place holder | 180 days | + | 986 | - |  | 2026-07-16
| place holder | 10 days | + | 996 | - |  | 2026-07-26
| EPA 30 Day review - prior to Public Comment Period | 45 days | + | 1041 | - |  | 2026-09-09
| Incorporte EPA edits | 30 days | + | 1071 | - |  | 2026-10-09
SIP/Reg Adoption Submission Schedule
|  |  |  | 1 |  |  | SIP Finished, release
| Release SIP/Regulations (49 days) | X*+X days |  |  |  |  | 2026-11-03
| Date for hearing date request | X | + | 25 |  |  | 2026-11-28
| Hearings (federal requirement) | X | + | 32 | - | 37 | 2026-12-05 | - | 2026-12-10
| Question ending date | X | + | 37 | - |  | 2026-12-10
| Post response to questions | X | + | 48 | - |  | 2026-12-21
| Public Notice Ends | X | + | 49 | - |  | 2026-12-22
| Response to Comments | 30 days | + | 80 | - |  | 2027-01-22
| Review and Adoption by Commissioner | 30 days | + | 110 | - |  | 2027-02-21
| DOL Review/Review committee (6 months) | Give to DOL | + | 290 | - |  | 2027-08-20
| DOL Review Completed (10 days) |  | + | 300 | - |  | 2027-08-30
| File by Lt. Gov | 14 days | + | 314 | - |  | 2027-09-13
| Send Filed Regulations and SIP to EPA | 30 days | + | 344 | - |  | 2027-10-13
Local
|  | X | + | 1 | - |  | 2026-11-03
|  | 30 days | + | 41 | - |  | 2026-12-14
|  | 14 days | + | 55 | - |  | 2026-12-28
|  | 14 days | + | 69 | - |  | 2027-01-11
|  |  | + | 76 | - |  | 2027-01-18
|  | 14 days | + | 90 |  |  | 2027-02-01 |  |  | +